## Project Planner
Project Planner
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 11 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
| Login (Steven) | 1 | 1 | 1 | 2 | 100% | bar: PERIODS 1 to PERIODS 2
| Logout (Steven) | 1 | 1 | 1 | 2 | 100% | bar: PERIODS 1 to PERIODS 2
| Create User (Steven) | 1 | 1 | 1 | 2 | 100% | bar: PERIODS 1 to PERIODS 2
| Delete User (Inderpreet Singh) | 2 | 3 |  |  | 50% | bar: PERIODS 2 to PERIODS 5
| Search Bar (Inderpreet Singh) | 4 | 2 |  |  | 85% | bar: PERIODS 3 to PERIODS 5
| My Shopping Cart (Christian) | 3 | 4 |  |  | 0% | bar: PERIODS 1 to PERIODS 2; PERIODS 4; PERIODS 6
| My Wish list (Christian) | 5 | 4 |  |  | 0% | bar: PERIODS 1; PERIODS 4; PERIODS 6; PERIODS 8
| Return Policy (Joe) | 5 | 2 |  |  | 100% | bar: PERIODS 2 to PERIODS 5
| Discount Promotions | 3 | 2 |  |  | 75%
| Stock Check (Steven) | 1 | 3 | 1 |  | 33% | bar: PERIODS 1 to PERIODS 2
| User Reviews | 6 | 1 |  |  | 60%
| User Profiles (Christian) | 9 | 3 |  |  | 0% | bar: PERIODS 2 to PERIODS 3; PERIODS 8; PERIODS 10
Non Func | Dark Mode | 9 | 6 |  |  | 50%
| Intearctive UI | 9 | 16 |  |  | 0% | bar: PERIODS 9 to PERIODS 16
| Multi-browser Support | 9 | 4 |  |  | 1%
| Low Latency, Fast performance | 10 | 5 |  |  | 80%
| Feature 17 | 11 | 2 |  |  | 0%
| Feature 18 | 12 | 6 |  |  | 0%
| Feature 19 | 12 | 1 |  |  | 0%
| Feature 20 | 14 | 5 |  |  | 0%
| Feature 21 | 14 | 8 |  |  | 44%
| Feature 22 | 14 | 7 |  |  | 0%
| Feature 23 | 15 | 4 |  |  | 12%
| Feature 24 | 15 | 5 |  |  | 5%
| Feature 25 | 15 | 8 |  |  | 0%