## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 11 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | 100% Complete
Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Login (Steven) | 1 | 1 | 1 | 3 | 100% | bar: PERIODS 1 to PERIODS 3
Logout (Steven) | 1 | 1 | 1 | 3 | 100% | bar: PERIODS 1 to PERIODS 3
Create new account (Steven) | 1 | 1 | 1 | 3 | 100% | bar: PERIODS 1 to PERIODS 3
Delete Account (Inderpreet Singh) | 3 | 3 | 3 | 4 | 100% | bar: PERIODS 2 to PERIODS 6
Search Bar (Inderpreet Singh) | 3 | 2 | 3 | 4 | 100% | bar: PERIODS 2 to PERIODS 6
Navbar ( Christian) | 3 | 3 | 3 | 4 | 100% | bar: PERIODS 2 to PERIODS 6; PERIODS 8; PERIODS 10
My Shopping Cart (Christian) | 3 | 4 | 3 | 4 | 100% | bar: PERIODS 2 to PERIODS 6
Return Policy (Joe) | 2 | 2 | 2 | 4 | 100% | bar: PERIODS 2 to PERIODS 5
Discount Promotions (Inderpreet Singh) | 7 | 2 | 7 | 4 | 100% | bar: PERIODS 2; PERIODS 4; PERIODS 6 to PERIODS 10
Stock Check (Steven) | 7 | 3 | 7 | 4 | 100% | bar: PERIODS 2 to PERIODS 4; PERIODS 6 to PERIODS 10
User Reviews (Joe) | 9 | 2 | 9 | 3 | 100% | bar: PERIODS 2; PERIODS 4; PERIODS 6; PERIODS 9 to PERIODS 11
User Profiles (Christian) | 10 | 4 | 10 | 5 | 100% | bar: PERIODS 2; PERIODS 4 to PERIODS 6; PERIODS 8; PERIODS 10 to PERIODS 14
Wish list (Steven) | 10 | 4 | 9 | 7 | 100% | bar: PERIODS 2; PERIODS 4; PERIODS 6; PERIODS 10 to PERIODS 16
Checkout (Singh) | 11 | 4 | 7 | 6 | 100% | bar: PERIODS 2; PERIODS 4; PERIODS 6 to PERIODS 8; PERIODS 11 to PERIODS 16
Support Page (Singh) | 12 | 5 | 12 | 5 | 100% | bar: PERIODS 2; PERIODS 4; PERIODS 6; PERIODS 8; PERIODS 12 to PERIODS 16
[Non functional Requirements]
Meet the teams git hub account (Sigh) | 13 | 3 | 13 | 4 | 100% | bar: PERIODS 2; PERIODS 4; PERIODS 6; PERIODS 8; PERIODS 12 to PERIODS 16
Interactive User interface (Christian) | 14 | 2 | 14 | 3 | 100% | bar: PERIODS 12; PERIODS 14 to PERIODS 16
Function on multiple browsers (Joe) | 14 | 2 | 14 | 3 | 100% | bar: PERIODS 12; PERIODS 14 to PERIODS 16
Low latency/Fast performance (Steven) | 15 | 1 | 15 | 2 | 100% | bar: PERIODS 12; PERIODS 14 to PERIODS 16
Sliding sections on the home page (Singh) | 15 | 1 | 15 | 2 | 100% | bar: PERIODS 15 to PERIODS 16